## RAID Log
ID | Type | Category | Description | Likelihood | Impact | Sprint / Module | Owner | Mitigation / Response | Status
R1 | Risk | Ethical/Bias | Algorithmic bias via race, age, or payer-type proxies in the risk score | Medium | High | Sprint 2 (Module 4) | Analyst (Grace) | Fairlearn subgroup audit (recall, FNR by race/age/gender); Ethics Panel review before model is finalized | Open
R2 | Risk | Privacy | Re-identification via combined demographic + clinical quasi-identifiers | Low | High | Sprint 1 (Module 3) | Analyst (Grace) | No external data merging; k-anonymity suppression (k=5) on subgroup reporting; identifiers dropped pre-modeling | Open
R3 | Risk | Adoption | Discharge planning staff distrust or ignore a 'black box' risk score | Medium | Medium | Sprint 3 (Module 5) | Analyst (Grace) | SHAP explainability layer; human-override path built into dashboard design | Open
R4 | Risk | Technical | Severe missingness in weight, payer_code, max_glu_serum corrupts model input | Medium | Medium | Sprint 1 (Module 3) | Analyst (Grace) | Drop fields with >90% missingness rather than impute; document decision in data dictionary | Open
R5 | Risk | Technical | Data leakage from repeat patient encounters inflates model performance | Medium | High | Sprint 1 (Module 3) | Analyst (Grace) | Patient-level (not encounter-level) train/test split | Open
R6 | Risk | Regulatory | Non-compliance if project is ever extended to real EHR data | Low (now) | High | Final Project | Analyst (Grace) | IRB and data-use agreement flagged as a precondition for any live deployment | Open
A1 | Assumption | Data | The Diabetes 130-US Hospitals dataset is representative enough of readmission drivers to demonstrate the methodology | — | Medium | Sprint 1 (Module 3) | Analyst (Grace) | State explicitly as a documented limitation; do not claim current clinical validity | Active
A2 | Assumption | Capacity | Discharge planning teams can realistically follow up with ~15% of weekly discharges | — | Medium | Sprint 2 (Module 4) | Analyst (Grace) | Revisit shortlist size if lift-over-baseline results suggest a different capacity threshold is more actionable | Active
A3 | Assumption | Technical | Open-source tooling (scikit-learn, SHAP, Fairlearn, Streamlit) is sufficient without paid infrastructure | — | Low | All sprints | Analyst (Grace) | Confirm no course requirement mandates a paid cloud platform before Final Project deployment | Active
I1 | Issue | Scope | Citation format instructed by course brief (NXU) vs. requested override (APA) creates ambiguity | — | Low | Module 1 (carried forward) | Analyst (Grace) | Confirm with instructor whether NXU format is a hard requirement before final submission | Open
I2 | Issue | Documentation | AI Disclosure Form content must reflect genuine personal reflection, not be drafted wholesale by AI | — | Medium | All modules | Analyst (Grace) | Draft disclosure content personally using conversation history as raw material only | Open
D1 | Dependency | Technical | Model development (Sprint 2) depends on clean, cohort-filtered data from Sprint 1 | — | High | Sprint 1 → Sprint 2 | Analyst (Grace) | Sprint 1 must pass a data-quality checklist before Sprint 2 modeling begins | Not started
D2 | Dependency | Technical | Dashboard (Sprint 3) depends on finalized SHAP and Fairlearn outputs from Sprint 2 | — | High | Sprint 2 → Sprint 3 | Analyst (Grace) | Freeze model version (SemVer tag) before dashboard integration begins | Not started
D3 | Dependency | External | Final Project deployment depends on Streamlit Community Cloud availability/free-tier limits | — | Medium | Final Project | Analyst (Grace) | Identify a fallback host (e.g., local demo) if free-tier limits block deployment | Not started

## Legend
Technical RAID Log — Legend & Notes
Type | Meaning
Risk | A potential future event that could negatively affect the project
Assumption | Something taken as true for planning purposes, not yet verified
Issue | A current, active problem requiring resolution now
Dependency | A task or deliverable that relies on another task completing first
Source | Rows R1–R4 and R6 are carried forward and expanded from the Module 1 Ethical Risk Register; R5 and all Assumptions/Issues/Dependencies are new to this Module 2 planning document.